## Table
Hearing_RFI | Minute | Paragraph No. | Sub_Task_No. | Task_Details | Task Completed? | Summary | >50% PROGRESSED
WWLA_Task_No. |  |  |  |  | Yes/No |  | <50% PROGRESSED
Surface water MALF Effects
1 | 2 | WWLA_Table_1 | 1(a) | Effects analysis on surface water bodies for all AEEs updated to reflect 2020 model data using Naturalised Scenario as baseline for comparison. | Yes | WWLA Supplementary Evidence dated 28/09/2020 contains this analysis. Neither the task nor the analysis were discussed specifically during JW conferencing, although DoC still expressed concerns about the possible impact on flows during low flow times.
| 2 | WWLA_Table_1 | 1(b) | Map showing surface water bodies in the area of proposed takes. | Yes | Has been incorporated into Areas of Interest Map agreed by the experts.
| 2 | 4(c) | 1(c) | With respect to Policy H.5 of the pRPN, an assessment of each application in terms of their “Hydraulic Connection Category” | Yes | WWLA Supplementary Evidence dated 28/09/2020 contains the analysis directed. However, DoC has expressed concerns about possible impacts on river flows, and wetland and dune lake levels irrespective of categorisation under Policy H.5.
| 2 | DoC_Add_7 | 1(d) | Stream depletion effects/Lakes: site-specific investigations on potential stream flow depletion/lake water level for high risk areas (with highest known ecological values + hydraulic connection). Concurrent flow gaugings (streams)/lake water level loggers in conjunction with pump tests. Note that there are a number of pre-existing GW takes in some areas that could be used to run these investigations before any well is dug. It would be useful to review the AEEs for these takes to see what assessment was undertaken. | No | Positions documented in Paragraphs 24 to 30 of JWS dated 27 Nov 2021. Further discusssion occurred and is documented in the JWS dated 11/12/2020 for conferencing which took place on 01/12/2020. This JWS of 11/12/20 documents that the experts agreed that shallow aquifer monitoring is a pragmatic means by which to establish potential effects of deep groundwater pumping on surface water bodies but that the adequacy of the monitoring proposed in terms of number of locations and freqeuncy and timing of any data collection is not sufficiently established for the protection of surface waters.
| 2 | DoC_Add_5 | 1(e) | Identify example spring(s) (in discussion with iwi/NRC/DOC) for which baseline data (water level monitoring) occurs prior to any abstraction. Further survey/monitoring required should consents be granted. | No | This task was not addressed as a separate task but was instead packaged into the overall discussions on effects on surface waterbodies.
General Head Boundary
2 | 2 | WWLA_Table_1 | 2(a) | Schematic drawing illustrating general head boundary in MODFLOW showing model layers, conductance values and average groundwater pressure. | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 2).
| 2 | WWLA_Table_1 | 2(b) | Hydrographs of groundwater level and constant/general head flux for L1-L6 at model cell corresponding to Waterfront bore location.
| 2 | 4(a) | 2(c) | The time series of the flux across the boundary should ideally be shown at a selection of high risk points (i.e. closest to major abstractions as well as places where saline intrusion is already occurring) in addition to the Waterfront bore location that is currently proposed.
Basement Topography
3 | 2 | WWLA_Table_1 | 3(a) | Comparison of basement topography in Lincoln Agritech Report to bore log data focused on area NW of Houhora-showing that LA analysis is >100m greater depth to basement than has been documented. | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 3).
Material Compressibility for Subsidence
4 | 2 | WWLA_Table_1 | 4(a) | Review of compressibility values used for settlement analysis WRT peat, clay, other materials. | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 4).
Drawdown at FNDC bore
5 | 2 | WWLA_Table_1 | 5(a) | Compare drawdown at FNDC bore in AEE to PDP table in peer review. | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 5).
Potential Wetlands Risk Analysis
6 | 2 | WWLA_Table_1 | 6(a) | Preparation of maps using the LiDAR showing potential wetlands and risk defined by degree of hydrologic connection and degree of drawdown. | Yes | This task was the subject of previous discussions between the experts, particularly on 05/10/2020 where notes on that session were circulated but had not been agreed to and signed by all participants. The JWS from expert conferencing held on 27/11/2020 records discussions on this task at Paragraphs 13-20. The JWS dated 16/12/2020 contains the experts' final agreed list of Areas of Interest (AOI) which are noted as circles on maps subject to the proviso that these circles are indicative guidelines and that nearby sites identified as having significance during benchmarking may be carried forward into the GMCP's.
| 2 | DoC_Add_1 | 6(b) | Ground truthing to be undertaken on high risk wetlands identified from the analysis. This could be undertaken from the short listed at risk sites, with preference given to the unmapped wetlands (not in FENZ etc). This should occur before groundwater monitoring bores are established. | No | The following is "Agreed text" from JWS dated 27/11/2020 (at Page 6), "For all of the listed potential wetland areas, a report is to be prepared by suitably qualified, independent expert(s) to ground-truth the extent of the wetland area(s) and to carry out an ecological survey describing the existing flora and fauna. The report is to assess the importance of each wetland and the level of risk." In the JWS dated 27/11/2020, DoC's expert is documented as agreeing that ground-truthing could be a part of the GMCP as an adaptive management type clause but defers the specificity of this to the planning conferencing (at Paragraph 19, Page 6).
| 2 | DoC_Add_2 | 6(c) | Ground truthing should also evaluate why some wetland sites classified as high risk did not pick up nearby connected wetlands, which presumably could be due to discrepancies in the GIS based approach (and groundwater modelling outputs). An example of this is in the document ‘WWLA_memo_depression_assessment_29092020’.pdf, Area of interest F (page 7) and K (page 14). This may highlight that there are unmapped wetlands of high risk which haven’t been captured | No | An agreed Area of Interest Map set has been prepared (refer to the JWS dated 16/12/2020). The "Agreed text" from the 16/12/2020 JWS states, "...the experts’ final agreed list of AOIs is: Areas D, E, G, H, J, K M, N, P & Q, noting that the circles shown on the maps are considered indicative guidelines and nearby sites that are identified as having significance as a wetland during the benchmarking exercise may be carried forward in the GMCPs. The experts propose that this material be incorporated into the GMCP."
| 2 | DoC_Add_3 | 6(d) | An ecological assessment should be conducted on the selected high risk wetlands for monitoring of groundwater. This should include establishment of permanent vegetation plots, invertebrate, fish and bird surveys. This information should be re-assessed on 3-5 year intervals in conjunction with reviews of water level monitoring data. Selection of the groundwater monitoring sites in the selected wetlands should be in conjunction with a NRC or DOC wetland specialist. | No | The following is "Agreed text" from JWS dated 27/11/2020 (at Page 6), "For all of the listed potential wetland areas, a report is to be prepared by suitably qualified, independent expert(s) to ground-truth the extent of the wetland area(s) and to carry out an ecological survey describing the existing flora and fauna. The report is to assess the importance of each wetland and the level of risk." In the JWS dated 27/11/2020, DoC's expert is documented as agreeing that ground-truthing could be a part of the GMCP as an adaptive management type clause but defers the specificity of this to the planning conferencing (at Paragraph 19, Page 6).
| 2 | 5(a) | 6(e) | The hydrogeologists for the Applicant, NRC and DoC, together with DoC’s ecologist and, as necessary the Applicant’s and NRC’s ecologists, are to confer with the intention of developing an agreed plan to address the wetland issue. | Yes | The following is "Agreed text" from JWS dated 27/11/2020 (at Page 6), "For all of the listed potential wetland areas, a report is to be prepared by suitably qualified, independent expert(s) to ground-truth the extent of the wetland area(s) and to carry out an ecological survey describing the existing flora and fauna. The report is to assess the importance of each wetland and the level of risk." In the JWS dated 27/11/2020, DoC's expert is documented as agreeing that ground-truthing could be a part of the GMCP as an adaptive management type clause but defers the specificity of this to the planning conferencing (at Paragraph 19, Page 6).
| 3 | 5(b) & (c) | 6(f) | When that plan is sufficiently developed, planners for those parties are to confer to determine whether, in their opinion, the plan is sufficient for the purpose outlined in paragraph 4 above, or could be with further indicated refinement, and advise the Panel accordingly. Progress toward that end should be advised as part of the jointly agreed schedule of tasks and timeline required by paragraph 6 of Minute and Direction #2 due 28 September 2020 | No | Planners have not confered on the matters directed.
Further Consultation with Waiora Marae
7 | 2 | 2(b) | 7(a) | Further consultation with Waiora Marae in light of its submission on the hearing. | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 7).
Valic and Wataview water requirements
8 | 2 | 4(b) | 8(a) | Updated information should be provided on the Valic and Wataview water requirements based on the information in the Stanisich and Fulton submission | Yes | Sarah Ongley (Counsel for DoC) advised (by email dated 20/11/2020) that DoC does not need to be consulted further on this Task (Task 9).
Consent conditions and GMCP's
9 | 2 | 2(c)(i) | 9(a) | If the “new” consent applications within the Motutangi-Waiharara Water Users Group FMU are to be included without priority being “saved” for existing consent holders, as is proposed, confirmation from those existing consent holders that they accept that proposition and its implications in the event that abstraction reductions are required. | Yes | Modifications to the draft proposed GMCP to remove the crossover with the MWWUG consents, ie the Middle group will be subject to a separate set of conditions and GMCP. The only crossover will be where monitoring sites and/or trigger levels are common to Reference in the Middle group GMCP to the existing MWWUG consents as having priority in the context of recommencing take in the event of a reduction or cessation in response to TLs being exceeded.
| 2 | 2(c)(ii) | 9(b) | Mitigation for any adverse effect on existing bore users should the water level or pressure in their existing bore change materially. | Yes | The two-tier Trigger Level response as the contingency within the adpative management regime responds firstly to unusual readings in monitored data by requiring further investigation of abstractions around those monitoring sites followed by a secondary response to cut-back abstraction volumes if unusual readings continue. This trigger level plan ensures that adverse effects on existing bore users from the exercise of these takes are mitigated (Trigger-Level 1) or remedied (Trigger-Level 2).
| 2 | 2(c) | 9(c) | Further refinement of the consent conditions and respective Groundwater Monitoring and Contingency Plan | No | It is anticipated that the conferencing of Planners is needed to complete this task.
|  | DoC_Add_3 | 9(d) | Model sensitivity should be presented for other parameters, such as (but not limited to) the 1.4 m level assigned to open water evaporation. Model should be re-calibrated with a smaller catchment area and inclusion of groundwater (GW) inputs to evaluate if a calibration/validation is still possible with some groundwater contributions. GW contribution is not likely to be occurring at all wetland areas (given the mosaic across the wetland and some perched rainfall fed systems), however a sub-model should be trialed to represent a smaller catchment contributing to the large standing water body east of loggers KM3 and KM4, which should be the focus of the GW evaluation. | No | Expert's positions on this original sub-task are documented in Paragraphs 31 to 35 of the JWS dated 11/12/2020 for expert conferencing which took place on 27/11/2020. In summary, the positions at the 27/11/2020 conferencing were that; (a) Mr Williamson did not see how additional modelling would contribute to deciding the applications or setting any conditions; (b) Mr Hughes commented that additional sampling would not necessarily assist the Hearing Commissioners; (c) Mr Blyth commented that further data collection and refinement in the future would help improve the model where localised groundwater contributions to surface water may not be accounted for in the model. Mr Blyth, in agreement with the other experts, was given time to review DoC's position and subsequently circulated revised positions on the additional monitoring sought by DoC, including this sub-task, on 01/12/2020. Table 1 of the JWS dated 11/12/2020 contains the final positions of experts on the revised position of this sub-task by DoC. In response to the revised DoC positions on additional monitoring, Mr Williamson's position remains unchanged from that expressed during conferencing held 27/11/2020, while Mr Hughes provides clarification on the recommendations made with regard to the MWWUG Staged Implementation and Monitoring Programme (SIMPR) which are going to be implemented by Council going forward (see Table 1, Page 9 of the JWS dated 11/12/2020 for the recommendations).
|  | DoC_Add_4 | 9(e) | Further radon sampling in Kaimaumau Wetland over the peak of summer throughout the standing water body to the East of monitoring sites KM3 and KM4 (multiple samples across a grid area to capture a range of results, given if springs are present they may be localised). This may require helicopter or boat access (i.e. hovercraft). | No | Expert's positions on the original version of this sub-task are documented in Paragraphs 31 to 35 of the JWS dated 11/12/2020 for expert conferencing which took place on 27/11/2020. Mr Blyth, during this conferencing, surmises that while radon sampling rounds have been conducted, these were mostly from drains where groundwater signatures can be minimised so that they are undetectable. He therefore considers that water within the wetland needs to be sampled to absolutely exclude the propsect of localised groundwater upwellings. Mr Blyth, in agreement with the other experts, was given some time to review DoC's position on the additional monitoring sought and he subsequently circulated revised positions on the additional monitoring sought, including with respect of this sub-task, on 01/12/2020. Table 1 of the JWS dated 11/12/2020 contains the final positions of experts on the revised position of this sub-task by DoC. In response to the revised position put forward by DoC, Mr Williamson responds that radon sampling was done in the locations agreed by the experts in the JWS prepared as part of the MWWUG and refers to the memorandum prepared for that. He notes that the site 2km to the east of Bacica drain was not sampled due to access issues only, and concludes therefore that further sampling at this time does not assist the Commissioners.
|  | DoC_Add_6 | 9(f) | What does the Applicant propose regarding threatened species assessment given NZCPS Policy 11 /NPSFM 2020? | No | Expert conferencing discussion on this task is documented in the JWS dated 16/12/2020. A Threatened Species report was prepared by DoC's expert and contributions made by NRC's expert to this report. Mr Williamson and Mr West agreed that the report was useful for understanding what threatened species may be present in the area and that such species would be adversely affected if wet habitats were exposed to more frequent and longer droughts. However, Mr West and Mr Williamson did not agree that the GMCP provides sufficient protections over these values as in Mr West's opinion monitoring facilities are spaced too far apart. Mr Williamson explained that the monitoring sites are positioned according to risk either identified via submitter concerns or on the magnitude and extent of modelled drawdown. Mr Hughes responded that there are 27 monitoring sites additional to the monitoring required within production bores [NOTE: Review of the AOI Overview map shows 33 Shallow Monitoring Bores and 28 Deep Monitoring Bores). The remaining disagreement on this task is that until model certainty and effects on surface water can be adequately addressed, then DoC believe an assessment of threatened species across much of the Aupouri Peninsula is necessary while Mr Williamson and Ms Hansen consider that threatened species assessment is required within the confirmed AOI areas only.

## KEY
Task Development Identification | ID | Organisation
WWLA
Commissioner
DoC
Tasks not from WWLA_Table_1
| Abbreviations | Term
| DoC | Department of Conservation
| WWLA | Williamson Water & Land Advisory Limited
| NRC | Northland Regional Council